## Sheet1
Module | Test plan identifier | Introduction | Test items | Features to be tested | Features not to be tested | Approach | Item pass/fail criteria= | Suspension criteria and resumption requirements | Test deliverables | Environmental needs | Responsibilities | Staffing and training needs | Schedule | Risks and contingencies | Approvals
Sign in | tp_sign-in_v1 | Testing signin functionality on BrowserStack website | Login with username and password and check its working | check username and password,sign in button | Title of the page and icon of the page | Manual testing, Automation for Login, Cross-browser testing (Chrome, Firefox) | Pass: if signin is successful Fail: if signin is unsuccessful | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name
Search | tp_search_v2 | Testing search funtionality on BrowserStack website | Enter input in search | Multiple input in search, search button functionality | Page icon and product image | Manual testing, Automation for Entering an Item and Click for Search Button Cross-browser testing (Chrome, Firefox) | Pass: Page is redirected to search related products Fail: If Page is Redirecting to home or not correctly redirected to searched item | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name
Add to cart | tp_addcart_v3 | Testing Cart functionality on BrowserStack website | Add to cart, update quantity | Adding products, updating quantity, cart total calculation | Third-party payment service | Manual testing, Automation for adding to cart Cross-browser testing (Chrome, Firefox) | Pass: If item is added to cart Fail: if item is not added after clicking on add to cart | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name
Delete cart | tp_deletecart_v4 | Testing Cart functionality on BrowserStack website | Add to cart, update quantity, remove item, proceed to checkout | Adding products, updating quantity, removing products, cart total calculation | Third-party payment service | Manual testing, Automation for deleting from cart Cross-browser testing (Chrome, Firefox) | Pass: If item is we are able to delete it from cart Fail: if item is not t deleting if clicked on delete button | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name
Name and address | tp_address_v5 | Test shipping address, name functionality after checkout | firstname,last name,address,state,postal code,submit button | firstname,last name,address,state,postal code,submit button | Product details and page icon | Manual testing, Automation for Filling Details Cross-browser testing (Chrome, Firefox) | Pass: If the Fields are accepting correct inputs and are clickable Fail: If Fields are Accepting anything as Input | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name
category(i.e.vendors) | tp_category(i.e. vendors)_v6 | Testing products its displaying category wise and its functionalities | all categories products like apple, samsung,google, oneplus | all categories products like apple, samsung,google, oneplus | product image functionality ,terms and conditions | Manual testing, Automation for Selecting Brands Cross-browser testing (Chrome, Firefox) | Pass: Function behaves as specified in requirements Fail: Function behaves differently than expected or breaks critical flow | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name
Offers | tp_offers_v7 | testing whether offers are displayed or not | check whether offers on products are displayed or not | checking offers on products are displayed or not | Title of the page , icon of the page and terms and conditions | Manual testing, Automation for selecting Offers button in home page Cross-browser testing (Chrome, Firefox) | Pass: If Offers is redirecting to it’s offers page Fail: If Page is not redirecting to above or It’s redirecting to home page | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name
Orders | tp_orders_v8 | testing orders page | check whether previous orders are displayed on orders page | checking previous orders are displayed on orders page | Title of the page , icon of the page and terms and conditions | Manual testing, Automation for getting the orders history Cross-browser testing (Chrome, Firefox) | Pass: If orders page display the order history Fail: If Page not display the order history | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name
Favourites | tp_Favourites_v9 | testing Favourites page functionality | check Favourites page functionality while adding and removing products | checking Favourites page functionality on adding and removing products | Title of the page , icon of the page and terms and conditions | Manual testing, Automation for adding to cart and deleting from cart Cross-browser testing (Chrome, Firefox) | Pass: Item is selected and added to our Favourites Fail: After clicking the Wishlist(favourite) button if the item is not Shown in Favourites | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name
Privacy policy | tp_privacy_policy_v10 | testing privacy policy functioning | check whether privacy policy is displayed or not | checking privacy policy will display or not | Title of the page , icon of the page and terms and conditions | Manual testing, Automation for Scrolling Down and selecting Read more button Cross-browser testing (Chrome, Firefox) | Pass: If Read More is redirecting to it’s privacy policy page Fail: If Page is not redirecting to above or It’s redirecting to home page | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name
Subscription | tp_subscription_v11 | testing subscription field is accepting valid mailid or not | check whether subscription field is accepting valid mailid or not | checking subscription field with both valid and invalid mailid | Title of the page , icon of the page and terms and conditions | Manual testing, Automation for clicking subscription in home page Cross-browser testing (Chrome, Firefox) | Pass: If the field accepts valid email Fail: If the field accepts invalid email | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name
Logout | tp_logout_v12 | testing whether user can successfully logout or not | check whether user can successfully logout or not | checking user can successfully logout or not | Title of the page , icon of the page and terms and conditions | Manual testing, Automation for clicking Logout button in home page Cross-browser testing (Chrome, Firefox) | Pass: If Logout is making us to logout of the account Fail: If Button is functioning | NA | Test cases DocumentsTest cases Documents Test reports Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | windows 11pc, testlink, excel, browser chrome and firefox browser, network | Eswari(prepare test cases and test analysis reports) | Selenium webdriver(testers names) | 2025-08-28 | no risk | Manager name